## Go Live East-West
| 18 West | Ankit & Yang keep current
| July 20, 2026 per | [5 empty] | xx
|  |  | Active means = Extensiv system preset ready for planning, testing, imports etc. | [6 empty] | 1-Lite, 2-Medium, 3-Heavy
| Customer | WMS System Today | Status, System Instance Ready | Warehouse | Region | Planned Go-Live Date (Extensiv) | Actual Go Live Date (In Extensiv) | ID # | CSR Name (by Region) | Customer Complexity | EDI Heavy | Transactions Sept 2025 | First Transaction Date (by Region) | Regional CSR (Latest Order) | Regional First Transaction Date | Matched Extensiv Customer
1 | Swiss Madison | Exstensiv | Active | BLUNDELL2 | West |  | Sept 25, 2025. |  | Truly Squire |  |  |  | 2025-09-22 11:43 | Truly Squire | 2025-09-22 11:43 | Swiss Madison, LLC
1 | Swiss Madison | Exstensiv | Active | BLUNDELL2 | EAST |  | Sept 25, 2025. | [6 empty] | No Transaction | No Transaction | Swiss Madison, LLC
2 | Partake Brewing | Exstensiv | deactivate | Calgary/Burnaby |  |  | Jan 15, 2026. | [7 empty] | Account Deactivated - name changed to Phillip Brewing LP
3 | Eco Packaging | Exstensiv | Active | Calgary | West |  | Dec 13, 2025. | EP02 | Kelben Zhang |  |  |  | 2025-11-20 16:18 | Kelben Zhang | 2025-11-20 16:18 | Eco Packaging Inc.
3 | Eco Packaging | Exstensiv | Active | Calgary | East |  | Dec 13, 2025. | EP02 | Samrat Rana |  |  |  | 2025-08-28 17:13 | Samrat Rana | 2025-08-28 17:13 | Eco Packaging Inc.
4 | GAF Materials LLL dba GAF (National) | Exstensiv | Active | BLUNDELL2 | West |  | Dec 08, 2025. | GM01 | Morvarid Valizadeh | 1 |  | 39 | 2025-12-05 11:42 | Morvarid Valizadeh | 2025-12-05 11:42 | GAF Materials LLL dba GAF
4 | GAF Materials LLL dba GAF (National) | Exstensiv | Active | BLUNDELL2 | East |  | Dec 08, 2025. | GM01 | Damini Damini | 1 |  | 39 | 2025-12-05 20:13 | Damini Damini | 2025-12-05 20:13 | GAF Materials LLL dba GAF
5 | A-Sha Foods USA (National) | Exstensiv | Active | Meadow | West |  | Dec 21, 2025. | AS01 | Tim Zhang | 1 |  | 18 | 2025-12-16 16:25 | Tim Zhang | 2025-12-16 16:25 | A-Sha Foods USA.
5 | A-Sha Foods USA (National) | Exstensiv | Active | Meadow | East |  | Dec 21, 2025. | AS01 | Amritha Sunny | 1 |  | 18 | 2025-12-19 10:53 | Amritha Sunny | 2025-12-19 10:53 | A-Sha Foods USA.
6 | Chanel Canada ULC (National Account) | Exstensiv | Active | Burnaby | West |  | Jan 18, 2026. | CC08 | Miho Kasahara | 1 |  | 44 | 2026-01-16 15:08 | Miho Kasahara | 2026-01-16 15:08 | Chanel Canada ULC
7 | Calkins & Burke Limited (No inventory Cross Dock Account) | Exstensiv | Active | Burnaby |  |  | Jan 18, 2026. | CB01 | Jamie Wong | 1 |  | 7 | 2026-01-16 15:29 | Jamie Wong
8 | Galil Foods (No inventory Seasonal) | Exstensiv | Active | Burnaby |  |  | Jan 18, 2026. | GF01 | Eva/Devangi |  |  | 3 |  | Eva/Devangi
9 | Nuknuuk | Exstensiv | Active | BLUNDELL2 | East |  | Feb 8, 2026. | LG01 | Amy | 1 |  | 36 | 2026-06-09 13:56 | Amy | 2026-06-09 13:56 | Nuknuuk
10 | Trane U.S Inc. | Exstensiv | Active | BLUNDELL2 | West |  | Feb 8, 2026. | TR01 | Igor Moisseev | 1 |  | 28 | 2026-02-06 10:33 | Igor Moisseev | 2026-02-06 10:33 | Trane U.S Inc.
11 | Trillium Architectural Products Ltd | Exstensiv | Active | BLUNDELL2 | West |  | Feb 16,2026 | TA02 | Casper Chen | 1 |  | 20 | 2026-02-13 16:59 | Casper Chen | 2026-02-13 16:59 | Trillium Architectural Products Ltd
12 | Mustang Survival Corp. | Exstensiv | Active | BLUNDELL2 | West |  | Feb 16,2026 | MS01 | Morvarid Valizadeh | 1 |  | 15 | 2026-02-13 09:17 | Morvarid Valizadeh | 2026-02-13 09:17 | Mustang Survival Corp
13 | FortisBC Energy Inc - FEI | Exstensiv | Active | BLUNDELL2 | West |  | Feb 16,2026 | FE05 | Dharmin Petel | 1 |  | 20 | 2026-02-13 14:21 | Dharmin Petel | 2026-02-13 14:21 | FortisBC Energy Inc - FEI
14 | FortisBC Energy Inc - Pilot Rig | Exstensiv | Active | BLUNDELL2 | West |  | Feb 16,2026 | FE06 | Morvarid Valizadeh | 1 |  | 15 | 2026-02-13 15:14 | Morvarid Valizadeh | 2026-02-13 15:14 | FortisBC Energy Inc - Pilot Rig
15 | Mangrove Water Technologies Ltd | Exstensiv | Active | BLUNDELL2 | West |  | Feb 20,2026 | MW03 | Igor Moisseev | 1 |  | 2 | 2026-02-20 13:22 | Igor Moisseev | 2026-02-20 13:22 | Mangrove Water Technologies Ltd
16 | Pistaché Skincare LLC | Exstensiv | Active | BLUNDELL2 | West |  | Feb 20,2026 | PS05 | Morvarid Valizadeh | 1 |  | na | 2026-02-20 13:23 | Morvarid Valizadeh | 2026-02-20 13:23 | Pistaché Skincare LLC
17 | Waterline Marketing DBA CreamRight Products | Exstensiv | Active | National | West |  | Feb 27,2026 | WM01 | Morvarid Valizadeh | 1 |  | 93 | 2026-02-27 15:02 | Morvarid Valizadeh | 2026-02-27 15:02 | Waterline Marketing DBA CreamRight Products
17 | Waterline Marketing DBA CreamRight Products | Exstensiv | Active | National | East |  | Feb 27,2026 | WM01 | jay scime | 1 |  | 93 | 2026-02-27 19:09 | jay scime | 2026-02-27 19:09 | Waterline Marketing DBA CreamRight Products
18 | Clearwater Seafoods Limited Partnership | Exstensiv | Active | National | West |  | Feb 27,2026 | CS01 | Casper Chen | 1 |  | 6 | 2026-02-27 15:11 | Casper Chen | 2026-02-27 15:11 | Clearwater Seafoods Limited Partnership
18 | Clearwater Seafoods Limited Partnership | Exstensiv | Active | National | East |  | Feb 27,2026 | CS01 | Priya Sagar | 1 |  | 6 | 2026-02-27 18:59 | Priya Sagar | 2026-02-27 18:59 | Clearwater Seafoods Limited Partnership
19 | NetX inc | Exstensiv | Active | Meadow | West |  | March 6,2026 | NX01 | Casper Chen | 1 |  | 30 | 2026-03-06 14:05 | Casper Chen | 2026-03-06 14:05 | NetX inc
20 | Global Choice Products Inc. | Exstensiv | Active | Meadow |  |  | March 6,2026 | GC02 | Dharmin Patel | 1 |  | 23 |  | Dharmin Patel
21 | FortisBC Energy Inc - AMI | Exstensiv | Active | Meadow | West |  | March 6,2026 | FE04 | Jonathan Law | 1 |  | 15 | 2026-03-06 14:49 | Jonathan Law | 2026-03-06 14:49 | FortisBC Energy Inc - AMI
22 | Crane Worldwide Logistics Canada Corp. | Exstensiv | Active | Meadow | West |  | March 6,2026 | CW03 | Tim Zhang | 1 |  | 5 | 2026-03-06 15:49 | Tim Zhang | 2026-03-06 15:49 | Crane Worldwide Logistics Canada Corp.
23 | Follow Nature Inc | Exstensiv | Active | Meadow | West |  | March 6,2026 | FN01 | Soha Sabounchi | 1 |  | 3 | 2026-03-06 15:56 | Soha Sabounchi | 2026-03-06 15:56 | Follow Nature Inc
24 | Safe Catch, Inc | Exstensiv | Active | Meadow | West |  | March 6,2026 | SC06 | Jaeeun Lee | 1 |  | 3 | 2026-03-06 15:25 | Jaeeun Lee | 2026-03-06 15:25 | Safe Catch, Inc
25 | Tapio Tea Company | Exstensiv | Active | Meadow |  |  | March 6,2026 | TT04 | Kelben Zhang | 1 |  | 3 |  | Kelben Zhang
26 | Viana Inc | Exstensiv | Active | Meadow | West |  | March 13,2026 | VI01 | Amy Wang | 1 |  | 16 | 2026-03-13 08:57 | Amy Wang | 2026-03-13 08:57 | Viana Inc
27 | Barton International | Exstensiv | Active | Meadow | West |  | March 13,2026 | BM01 | Igor Moisseev | 1 |  | 3 | 2026-03-13 10:09 | Igor Moisseev | 2026-03-13 10:09 | Barton International
28 | Bear Down Brands | Exstensiv | Active | Meadow |  |  | March 13,2026 | VL01 | Amy Wang | 1 |  | 2 |  | Amy Wang
29 | Good Natured Products Packaging Brampton LP - B.C. | Exstensiv | Active | Meadow | West |  | March 13,2026 | GN02 | Komalpreet Kaur | 1 |  | 2 | 2026-03-13 10:10 | Komalpreet Kaur | 2026-03-13 10:10 | Good Natured Products Packaging Brampton LP - B.C.
30 | Heat Sealing | Exstensiv | Active | Meadow | West |  | March 19,2026 | HS01 | Komalpreet Kaur | 1 |  | 42 | 2026-03-19 11:05 | Komalpreet Kaur | 2026-03-19 11:05 | Heat Sealing
31 | Emerge Technologies Inc | Exstensiv | Active | Meadow | West |  | March 19,2027 | ET02 | Jamie Wong | 1 |  | na | 2026-03-23 10:34 | Jamie Wong | 2026-03-23 10:34 | Emerge Technologies Inc
32 | Joels Wholesale LLC | Exstensiv | Active | Meadow |  |  | March 19,2028 | JW02 | Vickie Cao | 1 |  | na |  | Vickie Cao
33 | West Coast Toys Ltd. | Exstensiv | Active | BLUNDELL2 | West |  | March 27,2028 | WC01 | Jaeeun Lee | 2 |  | 40 | 2026-03-27 15:11 | Jaeeun Lee | 2026-03-27 15:11 | West Coast Toys Ltd.
34 | Jobar International, Inc. | Exstensiv | Active | BLUNDELL2 | West |  | March 27,2028 | JI02 | Karla Herrera Buenrostro | 3 | 3 | 55 | 2026-03-20 12:40 | Karla Herrera Buenrostro | 2026-03-20 12:40 | Jobar International, Inc.
35 | FedEx Trade Networks Trans.&Broke. Inc. | Exstensiv | Active | Meadow | West |  | April 1,2026 | FD01 | Aoi Takigashira | 1 |  | 10 | 2026-03-31 17:14 | Aoi Takigashira | 2026-03-31 17:14 | FedEx Trade Networks Trans.&Broke. Inc.
37 | Hellofresh (GDE Grocery Delivery E-Services Canada (Factor) | Exstensiv | Active | National | East |  | April 1,2026 | HD01 | Sachini Fernando | 1 |  | na | 2026-04-01 07:40 | Sachini Fernando | 2026-04-01 07:40 | GDE Grocery Delivery E-Services Canada (Factor)
38 | Biktrix Enterprises Inc. | Exstensiv | Active | Meadow | West |  | April 8,2026 | BE03 | Aoi Takigashira | 2 |  | 15 | 2026-04-07 15:28 | Aoi Takigashira | 2026-04-07 15:28 | Biktrix Enterprises Inc.
39 | Tofino Kombucha Inc. | Exstensiv | Active | National | West |  | April 17,2026 | TK01 | automation | 2 |  | 26 | 2026-04-17 09:59 | automation | 2026-04-17 09:59 | Tofino Kombucha Inc.
39 | Tofino Kombucha Inc. | Exstensiv | Active | National | East |  | April 17,2026 | TK01 | Kartik Sharma | 2 |  | 26 | 2026-01-26 09:26 | Kartik Sharma | 2026-01-26 09:26 | Tofino Kombucha Inc.
40 | Fraser Valley Steel & Wire Ltd. | Exstensiv | Active | Meadow | West |  | May 14,2026 | FV01 | Dhruv Sawhney | 1 |  | 6 | 2026-05-14 12:29 | Dhruv Sawhney | 2026-05-14 12:29 | Fraser Valley Steel & Wire Ltd.
41 | LMS Reinforcing Steel Group | Exstensiv | Active | Meadow/Burnaby | West |  | May 14,2026 | LM02 | Dhruv Sawhney | 1 |  | 2 | 2026-05-14 14:10 | Dhruv Sawhney | 2026-05-14 14:10 | LMS Reinforcing Steel Group
42 | Victoria Distiller Inc. | Exstensiv | Active | BLUNDELL2 | West |  | June 12,2026 | VD02 | Dhruv | 2 |  | 2 | 2026-06-12 13:58 | Dhruv | 2026-06-12 13:58 | Victoria Distiller Inc.
43 | Arc'teryx Equipment | Exstensiv | Active | Burnaby | West |  | July 13,2026 | AE02 | Kelben Zhang | 1 |  | 5 | 2026-07-10 10:25 | Kelben Zhang | 2026-07-10 10:25 | Arc'teryx Equipment
44 | Zenpack Canada Inc. | Exstensiv | Active | National | West |  | July 21,2026 | ZC02 | Vickie Cao | 2 |  | 45 | 2026-07-10 09:52 | Vickie Cao | 2026-07-10 09:52 | Zenpack Canada Inc.
44 | Zenpack Canada Inc. | Exstensiv | Active | National | East |  | July 21,2026 | ZC02 | Sachini Fernando | 2 |  | 45 | 2026-07-10 18:36 | Sachini Fernando | 2026-07-10 18:36 | Zenpack Canada Inc.
45 | Takigawa Corp | Exstensiv | Active | Aldergrove | West |  | July 27,2026 | TC01 | Lilia Chan-created by client himself | 2 |  | 15 | 2026-07-24 14:52 | cordinating orders by Miho Kasahara | 2026-07-24 14:52 | Takigawa Corporation Japan
46 | Dekor Storyz | Exstensiv | Active | Blundell |  | Aug 6,2026 | DK01 |  | Morvarid Valizadeh | 1 |  | 23
47 | BestBuy BC | Exstensiv | Active | Aldergrove |  | Aug 10,2026 | BB03 | BB03 | Kate Tran
48 | Un Sogno Corp. | Exstensiv | Active | BLUNDELL2 |  | TBD | US03 | Waiting confirmation from client API Integration/ Retailer Label |  | 3 | 3 | na

## Warehouse move
Calgary moving to Rockyview Alb.
# | Customer | WMS System Today | Status, System Instance Ready | Warehouse | Region | Planned Go-Live Date (Extensiv) | Actual Go Live Date (In Extensiv) | ID # | CSR Name (by Region) | Customer Complexity | EDI Heavy | Transactions Sept 2025 | First Transaction Date (by Region) | Regional CSR (Latest Order) | Regional First Transaction Date | Matched Extensiv Customer | Last WMS Transaction Date
49 | Canvas Craft Industries Ltd. | Camelot |  | 290189TOWN | West |  |  | CC07 | Igor Moisseev | 1 |  | na |  |  |  |  | 2026-07-31
50 | ROAR Beverages Canada Corp | Camelot |  | 290189TOWN | West |  |  | RB02 | Kelben Zhang | 1 |  | 16 |  |  |  |  | 2026-08-05
51 | CDN Energy & Power Corp | Camelot |  | 290189TOWN | West |  |  | CE04 | Komalpreet Kaur | 1 |  | 38 |  |  |  |  | 2026-08-04
52 | Collective Packaging Co. | Camelot |  | 290189TOWN | West |  |  | CP05 | Idy Lee | 1 |  | 6 |  |  |  |  | 2026-07-06
53 | Global Appetite Inc. | Camelot |  | 290189TOWN | West |  |  | GA01 | Jaeeun Lee | 1 |  | na |  |  |  |  | 2026-08-07
54 | Hanchett Paper Co. dba Shorr Packaging Corp | Camelot |  | 290189TOWN | West |  |  | SP04 | Casper Chen | 1 |  | 43 |  |  |  |  | 2026-08-10
55 | Pinnacle Logistics Solutions LTD | Camelot |  | 290189TOWN | West |  |  | PL02 | Idy Lee | 1 |  | na |  |  |  |  | 2025-11-18
56 | TLC Marketing Inc | Extensiv |  | 290189TOWN | West |  |  | TM01 | Aoi Takigashira | 1 |  | na
57 | Cansew Inc. | Camelot |  | 290189TOWN | West |  |  | CI04 | Komalpreet Kaur | 3 |  | 53 |  |  |  |  | 2026-08-11
58 | Edoko Food Importers Ltd | Camelot |  | 290189TOWN | West |  |  | EF02 | Tim Zhang | 1 |  | 5 |  |  |  |  | 2026-08-10
59 | Silver Paw | Camelot |  | 290189TOWN | West |  |  | SP05 | Igor Moisseev | 3 |  | 13 |  |  |  |  | 2026-08-10
60 | La Cocina Foods | Camelot |  | 290189TOWN | West |  |  | LC02 | Komalpreet Kaur | 1 |  | 12 |  |  |  |  | 2026-04-29
61 | Packpro Systems Inc. (Calgary customer) | camelot |  | 290189TOWN | West |  |  | PS04 | Komalpreet Kaur | 1 |  | 14 |  |  |  |  | 2026-06-12
62 | PROPELL (ALBERTA) LTD. | Camelot |  | 290189TOWN | West |  |  | PT01 | Idy Lee | 1 |  | 65 |  |  |  |  | 2026-08-05
63 | TTE Technology Inc. dba TCL North America | Camelot |  | 290189TOWN | West |  |  | TC02 | Domini Domini | 1 |  | 15 |  |  |  |  | 2026-05-04
|  |  | Code | Name
|  | code in WMS is : | 290189TOWN | 290189 TownshipRd261 ROCKYVIEW
|  | Code in Extensiv: | 290189Rockyview
TLC Marketing Inc already migrated on extensive as Fedex Name
we have one Packpro Systems Inc. (Toronto customer) already deactivated on extensiv

## Future migration Plan
Complexity | Customer | WMS Client Code | CSR from Latest WMS Transaction | User ID | Last WMS Transaction Date | Last Document | Warehouse | Created By EDI?
Complexity 2 | M&S Accessory Network Corp | MS02 | Morvarid Valizadeh | MVALI | 2026-08-05 11:05 | S00447485 | BLUNDELL2 | Yes
Complexity 2 | Le Groupe Lemur Inc | LG02 | Japneet Kaur | JAPNEET | 2026-08-10 10:26 | RA1084 | CHTS-2929 | No
Complexity 2 | Grey Wolf Equipment Rentals Inc. | SS03 | Karla Herrera Buenrostro | Karla Herrera Buenrostro | 2026-07-20 13:07 | S00443194 | BLUNDELL2 | Yes
Complexity 2 | Silver Paw | SP05 | Igor Moisseev | IMOISSEEV | 2026-08-10 14:17 | RA1108 | 290189TOWN | No
Complexity 2 | Safdie & Co. Inc | SC03 | Miho Kasahara | MIHOK | 2026-08-10 13:12 | RA1104 | BURNABY | No
Complexity 2 | Kruger Products Inc | KP01 | Hannaneh Nazari | HNAZARI2 | 2026-08-06 10:51 | RA0910 | BURNABY | No
Complexity 2 | The Neil Jones Food Company | NE01 | Komalpreet Kaur | KKAUR | 2026-08-10 08:31 | S00448506 | MEADOW | No
Complexity 2 | Global Gourmet Foods (2020) Ltd | GG02 | Casper Chen | CACHEN | 2026-08-10 16:35 | RA1118 | MEADOW | No
Complexity 2 | 12352991 Canada Inc (“RJI”) | RH01 | Amy Wang | Amy Wang | 2026-08-10 08:57 | S00448515 | MEADOW | Yes
Complexity 2 | Bay and Bay Transportation Services, Inc. | BB07 | Dharmin Patel | DHARMINP | 2026-08-07 12:35 | RA1008 | MEADOW | No
Complexity 2 | Silver Hills Bakery | SH02 | Japneet Kaur | JAPNEET | 2026-08-10 11:14 | S00448677 | CHTS-2929 | No
Complexity 2 | Lantic Sugar | LS01 | Vickie Cao | VCAO | 2026-08-04 10:06 | S00447102 | MEADOW | No
Complexity 2 | Rochester Midland Corporation | RM01 | Casper Chen | CACHEN | 2026-08-10 11:16 | S00448678 | MEADOW | No
Complexity 2 | Broadway Subway Constructors General Partnership | BS03 | Neha Bindra | NBINDRA | 2026-08-10 09:32 | S00448644 | MEADOW | No
Complexity 2 | Houle Electric Ltd | HE01 | Jamie Tin Yan Wong | JWONG | 2026-08-04 11:44 | S00447172 | MEADOW | No
Complexity 2 | Globe Union Canada Inc. | GU01 | Jamie Tin Yan Wong | JWONG | 2026-08-05 10:08 | S00447444 | MEADOW | No
Complexity 2 | Solenis LLC Diversy, Inc. | SL03 | Kate Tran | KTRAN | 2026-08-04 09:40 | S00447087 | ALDERGROVE | No
Complexity 3 | Indigo | IN01 | Dharmin Patel | Dharmin Patel | 2026-08-11 06:18 | RA1144 | BURNABY | Yes
Complexity 3 | Mark Anthony Group Inc. | MA02 | Devangi Umatiya | Devangi Umatiya | 2026-08-10 17:51 | S00448832 | BURNABY | Yes
Complexity 3 | Molson Coors Brewing Company | ML01 | Dhruv Sawhney | DHRUVS | 2026-08-07 16:17 | S00448214 | BURNABY | No
Complexity 3 | MAG-Central City Brewers & Distillers | MA03 | Devangi Umatiya | DEVANGIU | 2026-08-07 14:22 | S00448178 | BURNABY | No
Complexity 3 | Bay Street Manufacturing (Health Guard) | BS04 | Kartik Sharma | KSHARMA | 2026-08-11 18:17 | S00448857 | 2510ROYAL | Yes
Complexity 3 | United States Luggage Company LLC:Briggs | US02 | Morvarid Valizadeh | Morvarid Valizadeh | 2026-08-11 07:32 | S00448869 | BLUNDELL2 | Yes
Complexity 3 | United States Luggage Company LLC | US01 | Nihar Patel | Nihar Patel | 2026-08-10 15:08 | RA1111 | BLUNDELL2 | No
Complexity 3 | Expeditors Canada Inc-Miles Industries Project | EC04 | Sagar Singh | SSINGH1843 | 2026-06-04 10:30 | IA22583 | CHTS-2929 | No
Complexity 3 | Specialized Bicycle Components | SB03 | Soha Sabounchi | SOHAS | 2026-08-10 15:46 | RA1114 | MEADOW | No
Complexity 3 | FIJI Water Company, LLC | FW01 | Soha Sabounchi | Soha Sabounchi | 2026-08-10 08:15 | S00448419 | MEADOW | Yes
Complexity 3 | STERNO, LLC | SN01 | Komalpreet Kaur | Komalpreet Kaur | 2026-08-10 08:30 | S00448505 | MEADOW | Yes
Complexity 3 | TPV USA Corp | TU01 | Kate Tran | Kate Tran | 2026-08-10 15:01 | S00448756 | MEADOW | Yes
Complexity 3 | Rize Bikes Inc. | RB01 | Morvarid Valizadeh | Morvarid Valizadeh | 2026-08-11 00:02 | S00448843 | BLUNDELL2 | Yes
Complexity 3 | Euro-line Appliances Inc. | EA01 | Morvarid Valizadeh | MVALI | 2026-08-07 14:26 | S00448180 | BLUNDELL2 | No
Complexity 3 | Refresco North America | RN01 | Hannaneh Nazari | HNAZARI2 | 2026-08-10 11:39 | IA23137 | BURNABY | No
Complexity 3 | Premier Coasts Trading Ltd | PC04 | Dhruv Sawhney | DHRUVS | 2026-08-10 21:00 | S00448830 | BURNABY | Yes
Complexity 3 | Plato Ferments Inc. | PF03 | Parisa Farhand | PFARHAND | 2026-01-20 12:04 | S00397858 | BURNABY | Yes
Complexity 3 | Crush Imports | CI02 | Dhruv Sawhney | DHRUVS | 2025-12-22 16:24 | S00391471 | BURNABY | No
Complexity 3 | ZIWI USA Inc | ZU01 | Soroor Salemi | SSALEMI | 2026-02-13 09:45 | IA21662 | BURNABY | No
Complexity 3 | Exquisite Drinks | EX01 | [5 empty] | No
Complexity 3 | Freshca Impex Corp. | FI02 | Dhruv Sawhney | DHRUVS | 2026-08-04 13:21 | S00447238 | BURNABY | Yes
Complexity 3 | Sunshine Paradise Development | SP06 | Dhruv Sawhney | Dhruv Sawhney | 2026-08-04 15:58 | S00447249 | BURNABY | Yes
Complexity 3 | Cansew Inc. | CI04 | Igor Moisseev | Igor Moisseev | 2026-08-11 07:21 | S00448862 | 290189TOWN | Yes
Complexity 3 | Naturally Homegrown Foods Ltd | NH01 | Miho Kasahara | Miho Kasahara | 2026-08-10 15:56 | S00448508 | CHTS-2929 | Yes
Complexity 3 | Curtis International Ltd | CI03 | Japneet Kaur | JAPNEET | 2026-04-23 08:28 | W00001466 | CHTS-2929 | No
Complexity 3 | Tiger Drylac | TD01 | Tim Zhang | TZHANG | 2026-08-07 12:55 | S00447979 | MEADOW | No
Complexity 3 | Hello Fresh | HF01 | Sachini Fernando | Sachini Fernando | 2026-08-11 06:51 | S00448861 | BC | Yes
All these right now are in WMS Camelot system

## NEw Onboarded-Extensiv
Client Name | Onboarding Date | Planned Warehouse | Matched Extensiv Customer | CSR (Latest Order Created By) | First Transaction Date | First Transaction Type | First Transaction Warehouse | Last Transaction Date | Last Transaction Type | Last Transaction Warehouse | Latest Order Date | Latest Order Transaction ID | Latest Order Warehouse | Match Confidence
Trident Naval Systems of Canada Inc. | 46085 | Burnaby | Trident Naval Systems of Canada Inc. | kate Tran | 46122.6802 | Order | 7185 Burnaby | 46219.4215 | Order | 7185 Burnaby | 46219.4215 | 45939 | 7185 Burnaby | Exact
Swany America Corp | 46087 | Meadow | Swany America Corp | [10 empty] | Not found
Vuly Canada Operations Corp | 46133 | National | Vuly Canada Operations Corp | Lily Chan | 46196.4237 | Order | 8335Meadow | 46241.4098 | Order | 8335Meadow | 46241.4098 | 50464 | 8335Meadow | Exact
NIMA Imports | 46148 | Meadow | NIMA Imports Inc | Johnny Araujo | 46168.4464 | Order | 8335Meadow | 46168.4464 | Order | 8335Meadow | 46168.4464 | 39834 | 8335Meadow | Exact
MULTIVAC Canada Inc. (West) | 46148 | Burnaby | Multivac Canada Inc. | Gurjeet Kaur | 46212.4209 | Order | 8470 Brampton | 46241.6917 | Order | 8470 Brampton | 46241.6917 | 50576 | 8470 Brampton | Exact
Cambridge-Lee Industries LLC | 46149 | Meadow | Cambridge-Lee Industries LLC | Lily Chan | 46240.5927 | Order | 8335Meadow | 46240.6089 | Order | 8335Meadow | 46240.6089 | 50243 | 8335Meadow | Exact
Posco International America Corp. | 46150 | Meadow | Posco International America Corp. | Eva Ng | 46206.4077 | Order | 8335Meadow | 46234.5207 | Order | 8335Meadow | 46234.5207 | 47995 | 8335Meadow | Exact
RRA Trucking Ltd | 46157 | Meadow |  | Miho Kasahara | [9 empty] | Not found
Merlin Solar Technologies | 46167 | Meadow | Emerge Technologies Inc | Jamie Wong | 46238.5289 | Order | 8335Meadow | 46238.6032 | Order | 8335Meadow | 46238.6032 | 48686 | 8335Meadow | Fuzzy 73%
TATA International | 46169 | Meadow | Jobar International, Inc. | Karla Herrera Buenrostro | 46233.6015 | Order | 16160 Blundell | 46241.4434 | Order | 16160 Blundell | 46241.4434 | 50489 | 16160 Blundell | Fuzzy 81%
Totally Bamboo | 46170 | Meadow | Hollywood Chairs dba Totally Bamboo | Jess Chen | 46233.549 | Order | 8335Meadow | 46233.549 | Order | 8335Meadow | 46233.549 | 47853 | 8335Meadow | Manual
Origin Sustainable | 46170 | National | Icon Global Supply Inc. dba Origin Sustainables | Nihar Patel | 46234.6066 | Order | 8335Meadow | 46241.4121 | Order | 8335Meadow | 46241.4121 | 50468 | 8335Meadow | Manual
Unistraw Corp | 46176 | Meadow | Unistraw Corp. | Kelben Zhang | 46227.6578 | Order | 8335Meadow | 46227.6578 | Order | 8335Meadow | 46227.6578 | 47040 | 8335Meadow | Exact
Calibre | 46185 | National | Calibre Sales Inc | Eva Ng | 46238.604 | Order | CHTS-2929 | 46238.604 | Order | CHTS-2929 | 46238.604 | 48690 | CHTS-2929 | Fuzzy 70%
Grey Jay Sales | 46195 | CH | Grey Jay Sales & Distribution LTD | Eva Ng | 46239.6781 | Order | CHTS-2929 | 46239.6781 | Order | CHTS-2929 | 46239.6781 | 49020 | CHTS-2929 | Manual
Rhenus Logistics Canada(Solaris Bus) | 46202 | Meadow | Rhenus Logistics Canada | Kelben Zhang | 46238.5086 | Order | 8335Meadow | 46238.5086 | Order | 8335Meadow | 46238.5086 | 48617 | 8335Meadow | Fuzzy 73%
Modextil | 46206 | National | Modextil Inc | Gurjeet Kaur | 46238.3678 | Order | 8470 Brampton | 46238.3678 | Order | 8470 Brampton | 46238.3678 | 48503 | 8470 Brampton | Exact
Bissett Fasteners Ltd. | 46206 | Meadow | Bissett Fasteners Ltd. | [10 empty] | Not found
Ardisam | 46216 | Calgary | Ardisam | Kelben Zhang | [9 empty] | Not found
Saint James Brands LLC | 46217 | National | Saint James Brands LLC | Lily Chan | 46239.3763 | Order | 8335Meadow | 46239.3763 | Order | 8335Meadow | 46239.3763 | 48864 | 8335Meadow | Exact
Tai Lung Manufacturing Ltd | 46217 | Calgary | Tai Lung Manufacturing Ltd | Kelben Zhang- Eva NG | [9 empty] | Not found
Conglom | 46218 | Calgary | Conglom | Idy Lee | [9 empty] | Not found
Vanderbilthc | 46220 | National | Vanderbilthc | Lily Chan | [9 empty] | Not found
Growl | 46234 | Meadow | Growl | Eva Ng | [9 empty] | Not found
BENTO INC. | 46235 | Calgary | BENTO INC. | Eva Ng | 46240.412 | Order | 290189 Rockyview | 46240.412 | Order | 290189 Rockyview | 46240.412 | 50154 | 290189 Rockyview | Exact
Swell Brandz Inc | 46235 | Calgary | Swell Brandz Inc | Eva Ng | [9 empty] | Not found
Canada Bread | 46235 | Calgary | Canada Bread Company Ltd | Kelben Zhang | 46240.649 | Order | 290189 Rockyview | 46240.649 | Order | 290189 Rockyview | 46240.649 | 50261 | 290189 Rockyview | Exact
Rockwool | 46235 | Calgary | Rockwool (Roxul Inc) | Kelben Zhang | 46238.5885 | Order | 290189 Rockyview | 46238.6012 | Order | 290189 Rockyview | 46238.6012 | 48685 | 290189 Rockyview | Fuzzy 73%
Wolseley Canada | 46235 | Calgary | Wolseley Canada Inc | Kelben Zhang | [9 empty] | Not found
Salvation Army | 46235 | Calgary | Salvation Army Thrift Store, NRO | Kelben Zhang | 46240.3946 | Order | 290189 Rockyview | 46240.4403 | Order | 290189 Rockyview | 46240.4403 | 50163 | 290189 Rockyview | Manual
NTD Apparel Inc | 46238 | National | NTD Apparel Inc | [10 empty] | Not found